## PROJECT PLAN
WORK PLAN (PROJECT PLAN) Objective: Complete Week activities, tests and milestones before respective deadlines | time axis 2024-07-21 to 2024-10-31
Category | Action item/Deliverables | Owner | Start Date | End Date | Status
Enrollment | Complete the VA Program | Me | 2024-09-22 | 2024-11-18 | Behind | 2024-09-22: Behind; 2024-09-23: Behind; 2024-09-24: Behind; 2024-09-25: Behind; 2024-09-26: Behind; 2024-09-27: Behind; 2024-09-28: Behind; 2024-09-29: Behind; 2024-09-30: Behind; 2024-10-01: Behind; 2024-10-02: Behind; 2024-10-03: Behind; 2024-10-04: Behind; 2024-10-05: Behind; 2024-10-06: Behind; 2024-10-07: Behind; 2024-10-08: Behind; 2024-10-09: Behind; 2024-10-10: Behind; 2024-10-11: Behind; 2024-10-12: Behind; 2024-10-13: Behind; 2024-10-14: Behind; 2024-10-15: Behind; 2024-10-16: Behind; 2024-10-17: Behind; 2024-10-18: Behind; 2024-10-19: Behind; 2024-10-20: Behind; 2024-10-21: Behind; 2024-10-22: Behind; 2024-10-23: Behind; 2024-10-24: Behind; 2024-10-25: Behind; 2024-10-26: Behind; 2024-10-27: Behind; 2024-10-28: Behind; 2024-10-29: Behind; 2024-10-30: Behind; 2024-10-31: Behind
Job search | Sign contracts with 3 clients | Me | 2024-11-19 | 2024-12-20 | Not started
VA Work | Start Working with client 1 | Me | 2024-11-04 | 2024-11-29 | Not started
Contract Renewal | Renew Current Contract | Me | 2024-10-15 | 2024-11-28 | Not started | 2024-10-15: Not started; 2024-10-16: Not started; 2024-10-17: Not started; 2024-10-18: Not started; 2024-10-19: Not started; 2024-10-20: Not started; 2024-10-21: Not started; 2024-10-22: Not started; 2024-10-23: Not started; 2024-10-24: Not started; 2024-10-25: Not started; 2024-10-26: Not started; 2024-10-27: Not started; 2024-10-28: Not started; 2024-10-29: Not started; 2024-10-30: Not started; 2024-10-31: Not started
LinkedIn Update | Update LinkedIn Profile | Me | 2024-11-04 | 2024-11-22 | In Progress
CV | Update My CV Education | Me | 2024-11-04 | 2024-11-22 | In Progress
Portfolio | Create Portfolio Site | Me | 2024-11-04 | 2024-11-22 | Not started
Add New Category | Add new task/action item | Mom